Group Members

BSSE23058 Zunaira Abdul Aziz

BSSE23026 Eashal Yasin

BSSE23003 Fatima Noorulain

BSSE23104 Fatima Khalid

ASSIGNMENT # 2

33. PSO

### Task (a) - Part 1: Function Point Analysis

#### 2.1 External Inputs (EI)

| Req. ID | EI Name | Data Elements (DETs) | RETs | DET Count | Complexity | FP |
| --- | --- | --- | --- | --- | --- | --- |
| FR-01 | Customer Registration | CNIC, Name, Phone, Vehicle Number, Customer Type (Fleet/Individual) | 1 (Customer Profile RET) | 5 | Low | 3 |
| FR-02 | POS Offline Transaction Queuing | Liters purchased, Fuel type, Amount, POS ID, Timestamp, Sync Flag | 2 (Transaction RET + Sync Queue RET) | 6 | Average | 4 |
| FR-03 | Batch Data Sync | Batch ID, Transaction List, Total Checksum, Station ID, Sync Status | 2 (Batch RET + Station RET) | 5 | Average | 4 |
| FR-04 | Points Calculation & Awarding | Purchase amount, Multiplier, Points Awarded, Customer ID, New Balance | 2 (Customer Profile + Loyalty Tier RETs) | 5 | Average | 4 |
| FR-05 | Point Redemption Authorization | OTP, Redemption amount, POS ID, Customer ID, Updated Balance | 1 (Redemption Log RET) | 5 | Low | 3 |

EI Total: (2 Low × 3) + (3 Average × 4) = 6 + 12 = 18 FP

#### 2.2 External Outputs (EO)

| Req. ID | EO Name | Data Elements (DETs) | RETs | DET Count | Complexity | FP |
| --- | --- | --- | --- | --- | --- | --- |
| FR-06 | Transaction SMS Notification | Customer Name, Points Awarded/Redeemed, Current Balance, Station Location | 2 (Customer Profile + Transaction RET) | 4 | Low | 4 |
| FR-07 | Fleet Manager Analytics Dashboard | Total fuel consumed, Points earned, Vehicle breakdown, Station heatmaps, Date range | 3 (Customer RET + Vehicle RET + Transaction RET) | 5 | Average | 5 |

EO Total: (1 Low × 4) + (1 Average × 5) = 4 + 5 = 9 FP

#### 2.3 Internal Logical Files (ILF)

| Req. ID | ILF Name | Record Types (RETs) | RET Count | DET Description | Complexity | FP |
| --- | --- | --- | --- | --- | --- | --- |
| FR-08 | Unified Customer Database | Customer Profile, Vehicle Log, Transaction History, Points Balance | 4 | Name, CNIC, Phone, Vehicle Make, Reg Number, Liters, Amount, Points, Tier Status, Registration Date (15+ DETs) | Average | 10 |

ILF Total: (1 Average × 10) = 10 FP

#### 2.4 External Interface Files (EIF)

| Req. ID | EIF Name | External Source | RET Count | DET Description | Complexity | FP |
| --- | --- | --- | --- | --- | --- | --- |
| FR-09 | SAP/ERP Financial Ledger | PSO Legacy SAP ERP | 2 (General Ledger RET + Point Liability RET) | Account ID, Daily Point Liability, Monetary Value, Station Reconciliation, Sync Timestamp (5 DETs) | Low | 5 |

EIF Total: (1 Low × 5) = 5 FP

#### 2.5 External Inquiries (EQ)

| Req. ID | EQ Name | Files Referenced | RET Count | DET Description | Complexity | FP |
| --- | --- | --- | --- | --- | --- | --- |
| FR-10 | Real-time Balance Inquiry | Unified Customer Database | 1 | Customer ID, CNIC, Current Points, Equivalent Rupee Value (4 DETs) | Low | 3 |

EQ Total: (1 Low × 3) = 3 FP

#### 2.6 UFP Summary

| FP Component | Requirements Mapped | Complexity Calculation | Count | FP Count |
| --- | --- | --- | --- | --- |
| External Inputs (EI) | FR-01, FR-02, FR-03, FR-04, FR-05 | Low: 2 × 3 = 6 Avg: 3 × 4 = 12 | 5 | 18 |
| External Outputs (EO) | FR-06, FR-07 | Low: 1 × 4 = 4 Avg: 1 × 5 = 5 | 2 | 9 |
| Internal Logical Files (ILF) | FR-08 | Avg: 1 × 10 = 10 | 1 | 10 |
| External Interface Files (EIF) | FR-09 | Low: 1 × 5 = 5 | 1 | 5 |
| External Inquiries (EQ) | FR-10 | Low: 1 × 3 = 3 | 1 | 3 |
| TOTAL UFP |  |  | 10 | 45 |

### Task (a) - Part 2: Functional and Non-Functional Requirements

10 Functional Requirements

| # | Requirement | FP Type | Description |
| --- | --- | --- | --- |
| FR-01 | Customer Registration | EI | Fuel station managers register new profiles via POS using CNIC, phone number, and vehicle details. |
| FR-02 | POS Offline Transaction Queuing | EI | If internet is lost, the local POS system logs the loyalty transaction locally, flagging it for future sync. |
| FR-03 | Batch Data Sync | EI | The local POS automatically pushes all queued offline transactions to the central server when network is restored. |
| FR-04 | Points Calculation & Awarding | EI | The Loyalty Engine calculates DigiCash points based on liters purchased and updates the customer's balance. |
| FR-05 | Point Redemption Authorization | EI | The system verifies OTP and point balance to authorize a discount on the current fuel purchase. |
| FR-06 | Transaction SMS Notification | EO | The CRM automatically triggers an SMS via a third-party gateway detailing points earned/spent and current balance. |
| FR-07 | Fleet Manager Analytics Dashboard | EO | Corporate clients can log in to view aggregated data on fuel consumption and points across their registered vehicle fleet. |
| FR-08 | Unified Customer Database | ILF | The central repository storing all demographic data, vehicle logs, tier statuses, and transaction histories. |
| FR-09 | SAP/ERP Financial Ledger | EIF | The CRM reads/writes aggregated financial point liabilities to PSO's existing SAP backend to ensure accounting accuracy. |
| FR-10 | Real-time Balance Inquiry | EQ | Station attendants can query a customer's CNIC to view their current point balance without executing a transaction. |

10 Non-Functional Requirements

| # | Requirement | Category | Description |
| --- | --- | --- | --- |
| NFR-01 | Offline Availability | Reliability | The POS module must retain up to 72 hours of offline transaction data without loss during prolonged outages. |
| NFR-02 | Scalability | Scalability | Must support concurrent data synchronization from up to 3,500+ retail outlets nationwide. |
| NFR-03 | Transaction Performance | Performance | Point redemption queries must resolve in < 2.5 seconds to prevent bottlenecks at fuel pumps. |
| NFR-04 | PII Security | Security | All CNIC and customer data must be encrypted at rest and in transit using AES-256 encryption. |
| NFR-05 | Legacy Hardware Compatibility | Usability | The local POS sync software must be lightweight enough to run on legacy Pentium-era hardware at rural stations. |
| NFR-06 | Regulatory Compliance | Compliance | System architecture and data storage policies must comply with State Bank of Pakistan (SBP) data privacy laws. |
| NFR-07 | ERP Integration Uptime | Reliability | The SAP integration bridge must maintain 99.9% uptime for daily financial reconciliations. |
| NFR-08 | Bilingual Interface | Usability | Customer-facing SMS alerts and printed POS receipts must support both Urdu and English text. |
| NFR-09 | Modular Updatability | Maintainability | The Loyalty Engine can be updated independently without taking the main Customer Database offline. |
| NFR-10 | Low-Bandwidth Sync | Performance | Data sync payloads must be compressed (<20KB per transaction) to work effectively over 2G/3G networks in remote areas. |

### Task (b) - COCOMO-II Early Design Modeling

1) Estimation of KLOC:

- Total UFP: 45

- Language Factor: The project involves a mix of legacy integration (C/C++) and modern backend/mobile (Java/C#). We use the industry-average conversion factor of 50 LOC per Function Point.

- Calculation: 45 × 50 = 2250 SLOC

- Conversion to KLOC: 2250 / 1000 = 2.25 KLOC

2) Scale Factors (SF):

| Scale Factor | Rating | Value | Reasoning & Context |
| --- | --- | --- | --- |
| PREC (Precedentedness) | Nominal | 3.72 | PSO operates massive logistics, but a centralized offline-first CRM interacting directly with end-consumers is a relatively new endeavor for them. |
| FLEX (Development Flexibility) | Low | 4.05 | High constraint. The system must rigidly adhere to SBP data regulations and predefined legacy SAP financial ledger formats. |
| RESL (Architecture / Risk Resolution) | High | 2.83 | As noted in Assignment 1, a detailed Risk Register has been developed, and connectivity risks are mitigated via the offline-first architecture. |
| TEAM (Team Cohesion) | Nominal | 3.29 | Mixed team of legacy IT staff, new mobile developers, and retail operations managers requiring heavy coordination. |
| PMAT (Process Maturity) | Nominal | 4.68 | Standard enterprise IT PMO standards apply. |

- SF Calculation:

B = 0.91 + 0.01 x (3.72 + 4.05 + 2.83 + 3.29 + 4.68)

B = 0.91 + 0.1857 = 1.0957

3) Effort Multipliers (EM):

| Effort Multiplier | Rating | Value | Reasoning & Context |
| --- | --- | --- | --- |
| RCPX (Product Reliability & Complexity) | High | 1.33 | System handles direct financial liabilities (DigiCash) and complex offline queuing (FR-02) across thousands of nodes. |
| RUSE (Developed for Reusability) | Nominal | 1.00 | Developed specifically for PSO's proprietary hardware and SAP setup; not intended for external resale. |
| PDIF (Platform Difficulty) | High | 1.29 | Must interface with highly constrained legacy POS hardware (NFR-05) and unstable 2G networks (NFR-10). |
| PERS (Personnel Capability) | Nominal | 1.00 | Standard, capable enterprise development team. |
| PREL (Personnel Continuity) | Nominal | 1.00 | Standard corporate retention expected throughout the 1-year development cycle. |
| FCIL (Facilities) | Nominal | 1.00 | Standard PSO corporate IT infrastructure and environments. |
| SCED (Required Schedule) | Nominal | 1.00 | Standard 12-month rollout as defined in the Assignment 1 business case. |

- EAF Calculation:

EAF = 1.33 x 1.00 x 1.29 x 1.00 x 1.00 x 1.00 x 1.00 = 1.7157

4) Final Effort Estimation:

- Formula: Effort = A x (KLOC)^B x EAF (Where A = 2.94 as per COCOMO II)

- Calculations:

(2.25)1.0957= 2.44

Effort = 2.94 x 2.44 x 1.7157

Effort = 12.30 Person-Months

5) Development Duration (Assuming a core team of 4 dedicated developers/analysts):

- Dev. Duration = 12.30 / 4 = 3.07 Months